## Test Cases
Test ID | Test name | Scenario / setup | Expected control outcome | Evidence to attach | Status
T01 | Joiner — Morgan HR | Morgan HR starts on 2026-09-01. Her manager requests Microsoft 365 and HRIS Contributor access. | The account is not provisioned before the start date. The manager and HRIS Owner approvals are documented before access is granted. | Fictional IAM ticket; approval record; target group list. | Planned
T02 | Mover — Alex Finance to Sales | Alex transfers from Finance Analyst to Sales Representative on 2026-09-15. | Finance Reader access is removed before Sales Standard access is added. Alex must not retain Finance Reader after the move. | Before-and-after group membership table; Entra audit-log screenshot when completed technically. | Planned
T03 | Leaver — Jamie Contractor | Jamie's approved contractor end date has passed, and there is no approved contract extension. | Jamie's account is disabled, active sessions are revoked, and all role-based groups are removed. | Leaver checklist; Entra audit-log screenshot when completed technically; exception note if delayed. | Planned

## Test Results
ERG — JML Test Results
Test ID | Test name | Result | Risk if the control failed | Evidence reviewed | Recommended improvement | Test status
T01 | Joiner — Morgan HR | Passed: The fictional request shows Morgan's 2026-09-01 start date. The manager requests Microsoft 365 and the HRIS Owner approves HRIS Contributor. IAM creates access only on the approved start date. | Morgan could receive sensitive HR access before she is an active employee, or without the correct approval. | Fictional ticket IAM-2026-001; manager approval; HRIS Owner approval; access catalogue entry for SG-APP-HRIS-HR-Contributor. | In a real environment, integrate the HR system with the IAM platform so the worker start date is validated automatically. | Complete — simulated; repeat in Entra lab
T02 | Mover — Alex Finance to Sales | Passed: The planned workflow removes SG-APP-ERP-Finance-Read before adding Alex to SG-APP-CRM-Sales-Standard. Alex retains only Microsoft 365 baseline access plus the Sales role. | Alex could retain unauthorized Finance access after moving to Sales, creating privilege creep and unnecessary exposure to financial data. | Access catalogue; JML workflow; planned before-and-after group membership record; Entra audit log to be captured in the Entra project. | In a real environment, use HR-triggered role-change workflows that compare current access to the target-role baseline and create an exception if old access remains. | Complete — simulated; repeat in Entra lab
T03 | Leaver — Jamie Contractor | Passed: The planned workflow blocks Jamie's sign-in, revokes active sessions, and removes Microsoft 365 and Service Desk group access after the contractor end date passes. | Jamie could continue accessing internal tickets or collaboration data after the contract ends. | JML workflow; access catalogue; planned leaver checklist; Entra audit log to be captured in the Entra project. | In a real environment, run a daily report for end dates and automatically create high-priority offboarding tasks for accounts still enabled after the end date. | Complete — simulated; repeat in Entra lab